## Sheet1
| Automated | [5 empty] | Manual
| Completed |  | Pending |  | Total |  | Completed | Pending | Total
Update | 1380 |  | 4108 |  | 5488 |  | 106 | 410 | 516
Delete | 0 |  | 554 |  | 554 |  | 8 | 85 | 93
Select | 0 |  | 5236 |  | 5236 |  | 0 | 326 | 326
Misc. | 0 |  | 52 |  | 52 |  | 0 | 250 | 250
| Update |  | Delete |  | Select |  | Misc.
| Automated | Manual | Automated | Manual | Automated | Manual | Automated | Manual
Completed | 1380 | 106 | 0 | 8 | 0 | 0 | 0 | 0
Pending | 4108 | 410 | 554 | 85 | 5236 | 326 | 52 | 250
Total | 5488 | 516 | 554 | 93 | 5236 | 326 | 52 | 250

## Sheet2
Story ID | Title | Started Dt | Status | Owner
168740360 | **SRs** make _Closed - No Response_ status function like _Closed_ | 2019-06-11 | Coding is done for 5 requirements. Need to confirm with Robert regrding type ID.Code Commit yet to do. | Swati/Sumitha
161103006 | prevent SR closure without at least 1 SR type and client/client id value | 2019-07-11 | Doubt has been clarified. Code commit yet to do | Remith/Smruti
147480193 | CP SR changes related to SLA Miss | 14/11/2019 | Dev tasks yet to create. White paper yet share with Client | Abhi/Sumitha
163393447 | **ClientProfile** - update SLA due date calculation for requests sent over the weekend | 18/11/2019 | Tasks and white paper yet to submit. | Nayak/Smruti